## Sayfa1
Task | Start Date | Days to Complete
Software Development Plan (SDP) | 2016-10-13 | 4
SDP v2 | 2016-10-17 | 3
Software Requirements Document (SRS) + Software Test Plan (STP) | 2016-10-20 | 4
SRS v2 and STP v2 | 2016-10-24 | 3
Software Design Document (SDD) | 2016-10-27 | 13
SDD v2 + implementation | 2016-11-09 | 19
Software Test Report (STR) + demo | 2016-11-28 | 11